## Sheet1
Tasks | Initial Planning | Revised planning | Setup MAIN | Setup GP | Setup OPT | Setup GUI | Setup SettingsPackage | Setup Manager | Setup Snapshots | Initial Documentation | Additional algorithms | Integrate: Manager-Snapshot | Integrate: Manager-GUI | Integrate: OPT-GP (and inbetween) | Initial Testing: Snapshot | Initial Testing: Snapshot | Initial Testing: GP | Initial Testing: OPT | Testing documentation | Design understandable presentation | Export GUI from Qt | Link GUI and SettingsPackage | OPT Revisions and Additions
Completed date | 2016-05-24 | 2016-05-27 |  | 2016-07-13 | 2016-07-01 | 2016-07-03 | 2016-07-12 | 2016-07-11 | 2016-07-12 | 2016-07-29 |  |  |  |  | 2016-07-28 | 2016-07-27 |  | 2016-07-28 |  |  | 2016-08-22 | 2016-08-23 | 2016-07-20
Completed week | 1 | 1 | -6072 | 8 | 6 | 6 | 8 | 8 | 8 | 10 | -6072 | -6072 | -6072 | -6072 | 10 | 10 | -6072 | 10 | -6072 | -6072 | 14 | 14 | 9 | -6072 | -6072 | -6072
Start date: | 2016-05-23
Total tasks | 21
Completed tasks
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 2 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 1 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total days | 154
Total weeks | 22
Theoretical tasks per week | 0.95455
Ideal (Weeks) | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 21 | 20.0455 | 19.0909 | 18.1364 | 17.1818 | 16.2273 | 15.2727 | 14.3182 | 13.3636 | 12.4091 | 11.4545 | 10.5 | 9.5455 | 8.5909 | 7.6364 | 6.6818 | 5.7273 | 4.7727 | 3.8182 | 2.8636 | 1.9091 | 0.95455 | 0
Actual (Weeks) | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 21 | 19 | 19 | 19 | 19 | 19 | 17 | 17 | 13 | 12 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
CURRENT CUTOFF